## Simple Safety Risk Register
TEAM: FREEZA RISK REGISTER
RISK DESCRIPTION | Probability | Impact | PRIORITY LEVEL | Severity | MITIGATION NOTES | OWNER
Give a brief summary of the risk. | Probability | Impact | Impact x Priority | Rating based on impact and likelihood | What can be done to lower or eliminate the impact or probability? | Who's responsible?
Project purpose and need is not well defined | 3 | 5 | 15 | HIGH | Complete a business case if not already provided and ensure purpose is well defined on Project Charter and PID. | Project Sponsor
Underestimated Resources Required | 3 | 4 | 12 | MEDIUM | Fully discuss ongoing Resource Needs during daily/weekly meetings | Project Sponsor and Team Members
Skill Gaps | 2 | 3 | 6 | MEDIUM | Analyze skills required at beginning of project and ensure team members meet requirements | Project Sponsor/Project Manager
Quality Control | 3 | 5 | 15 | HIGH | Ensure quality control checks are being completed during and after every Iteration | Team Members and Project Manager
Scope Creep | 2 | 5 | 10 | MEDIUM | Constant monitoring of project development and budget | Project Manager
Burnout | 4 | 4 | 16 | MEDIUM | Monitoring team members well being and keeping and distributing work load evenly | All Members