## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name | Freeza | Romaine, Bren, Sukh |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Romaine
Project Start Date: | 2024-02-19 |  |  |  |  | February | [13 empty] | March | [27 empty] | April | [29 empty] | May
Scrolling Increment: | 3 | time axis 2024-02-22 to 2024-05-30
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-02-22 to 2024-05-30
Iteration 1
Introductions and Iteration assess | Low Risk | Team | 100% | 2024-02-19 | 5
Planning meeting report | Low Risk | Team | 100% | 2024-02-22 | 7
Complete stakeholder register | High Risk | Team | 100% | 2024-02-29 | 11
Design/test three personas | Low Risk | Romaine, Bren, Sukh | 100% | 2024-03-11 | 10
Complete / review progress report | Med Risk | Team | 100% | 2024-03-13 | 8
Iteration 2
Complete all activities in Iteration | Goal | Team | 100% | 2024-03-21 | 40 | 2024-03-21: 2; 2024-03-22: 2; 2024-03-23: 2; 2024-03-24: 2; 2024-03-25: 2; 2024-03-26: 2; 2024-03-27: 2; 2024-03-28: 2; 2024-03-29: 2; 2024-03-30: 2; 2024-03-31: 2; 2024-04-01: 2; 2024-04-02: 2; 2024-04-03: 2; 2024-04-04: 2; 2024-04-05: 2; 2024-04-06: 2; 2024-04-07: 2; 2024-04-08: 2; 2024-04-09: 2; 2024-04-10: 2; 2024-04-11: 2; 2024-04-12: 2; 2024-04-13: 2; 2024-04-14: 2; 2024-04-15: 2; 2024-04-16: 2; 2024-04-17: 2; 2024-04-18: 2; 2024-04-19: 2; 2024-04-20: 2; 2024-04-21: 2; 2024-04-22: 2; 2024-04-23: 2; 2024-04-24: 2; 2024-04-25: 2; 2024-04-26: 2; 2024-04-27: 2; 2024-04-28: 2; 2024-04-29: 2
Planning meeting report | Low Risk | Team | 100% | 2024-03-23 | 7
Complete Resource Needs | Med Risk | Team | 100% | 2024-03-28 | 14
Create and manage Gantt Chart | On Track | Romaine | 100% | 2024-03-30 | 57
Implement GitHub features | On Track | Team | 100% | 2024-03-31 | 24
Iteration 3
Fully understanding GitHub basics | Goal | Team | 100% | 2024-05-01 | 29 | 2024-05-01: 2; 2024-05-02: 2; 2024-05-03: 2; 2024-05-04: 2; 2024-05-05: 2; 2024-05-06: 2; 2024-05-07: 2; 2024-05-08: 2; 2024-05-09: 2; 2024-05-10: 2; 2024-05-11: 2; 2024-05-12: 2; 2024-05-13: 2; 2024-05-14: 2; 2024-05-15: 2; 2024-05-16: 2; 2024-05-17: 2; 2024-05-18: 2; 2024-05-19: 2; 2024-05-20: 2; 2024-05-21: 2; 2024-05-22: 2; 2024-05-23: 2; 2024-05-24: 2; 2024-05-25: 2; 2024-05-26: 2; 2024-05-27: 2; 2024-05-28: 2; 2024-05-29: 2
Planning meeting report | Low Risk | Team | 100% | 2024-05-04 | 26
Complete Risk Register | Med Risk | Team | 100% | 2024-05-19 | 7
KanBan Board | Low Risk | Bren | 100% | 2024-05-21 | 9
Integrate code, push to Github, review integration | High Risk | Team | 100% | 2024-05-23 | 3
Complete user acceptance testing | High Risk | Sukh | 100% | 2024-05-24 | 6

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-29 |  |  |  |  | May | [6 empty] | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2024-05-30 to 2024-07-24
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-29 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2024-06-03 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2024-05-26 | 10
Task 4 | Milestone |  |  | 2024-06-18 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2024-06-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-04 | 13
Task 2 | On Track |  | 50% | 2024-06-06 | 9
Task 3 | Low Risk |  | 33% | 2024-06-11 | 11
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: T
Task 5 |  |  |  | 2024-06-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-13 | 4
Task 2 | Med Risk |  |  | 2024-06-16 | 14
Task 3 | On Track |  |  | 2024-07-01 | 6
Task 4 | Goal |  |  | 2024-07-05 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2024-06-04 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-08 | 15
Task 2 |  |  |  | 2024-07-22 | 5
Task 3 | Milestone |  |  | 2024-09-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-29 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2024-06-03 to 2024-07-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-03 to 2024-07-28
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-29 | 3
Task 2 | Milestone |  |  | 2024-06-03 | 1 | bar: 2024-06-03
Task 3 | Low Risk |  | 50% | 2024-05-26 | 10
Task 4 | Milestone |  |  | 2024-06-18 | 1 | bar: 2024-06-18
Task 5 | Med Risk |  | 10% | 2024-06-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-04 | 13
Task 2 | On Track |  | 50% | 2024-06-06 | 9
Task 3 | Low Risk |  | 33% | 2024-06-11 | 11
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: 2024-06-13
Task 5 |  |  |  | 2024-06-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-13 | 4
Task 2 | Med Risk |  |  | 2024-06-16 | 14
Task 3 | On Track |  |  | 2024-07-01 | 6
Task 4 | Goal |  |  | 2024-07-05 | 3 | 2024-07-05: 2; 2024-07-06: 2; 2024-07-07: 2
Task 5 | Low Risk |  |  | 2024-06-04 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-08 | 15
Task 2 |  |  |  | 2024-07-22 | 5
Task 3 | Milestone |  |  | 2024-09-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one